## Overall Plan
Day # | Date | Topics | Primary Owner | Secondary Owner | Status | Remarks
Day #0 | 2022-08-12 | Deck Preparation | Shan |  | DONE
Day #0 | 2022-08-12 | Meeting Schedule | Organizers |  | DONE
Day #0 | 2022-08-12 | WhatsApp Group Creation | Team | Shan/Satish | DONE
Day #1 | Objective | Write Simple Console based Hello World Program in VS Code | Team | Shan/Satish | Not Done
Day #1 | 2022-08-16 | Team Introductions | Team | Shan/Satish | Not Done
Day #1 | 2022-08-16 | Prerequisites | Team | Shan/Satish | Not Done
Day #1 | 2022-08-16 | Environment Setup – VS Code Installation | Team | Shan/Satish | Not Done | IT Team help needed
Day #1 | 2022-08-16 | Environment Setup – Dot net SDK Installation | Team | Shan/Satish | Not Done | IT Team help needed
Day #1 | 2022-08-16 | Environment Setup – Visual C++ Redistributable for Visual Studio 2015 | Team | Shan/Satish | Not Done | IT Team help needed
Day #1 | 2022-08-16 | Environment Setup – Git Repository | Team | Shan/Satish | Not Done | IT Team help needed
Day #1 | 2022-08-16 | Live exercise #1 – Hello World Program (C# Console App) | Shan | Team/Satish | Not Done
Day #1 | 2022-08-16 | Learn about Hello World Program, Build and Run | Shan | Team/Satish | Not Done
Day #1 | 2022-08-16 | Learn about, Git Initialization, code check-in, Repository Browsing | Shan | Team/Satish | Not Done
Day #1 | 2022-08-16 | Lab exercise #1 – Write any Simple Program | Team | Shan/Satish | Not Done | IT Team help needed
Day #2 | Objective | Write Simple MS Tests for a Calculator Class in VS Code | Team | Shan/Satish | Not Done
Day #2 | 2022-08-17 | Live exercise #2 – Simple MS Test Program | Shan | Team/Satish | Not Done
Day #2 | 2022-08-17 | Learn about creating Class Librarires, adding main program | Shan | Team/Satish | Not Done
Day #2 | 2022-08-17 | Learn about MS Test Program, Build and Run | Shan | Team/Satish | Not Done
Day #2 | 2022-08-17 | Learn about MS Test Lifecycle Methods, Build and Run | Shan | Team/Satish | Not Done
Day #2 | 2022-08-17 | Learn about MS Test Program, Build and Run, , Linking Projects to Solution, Adding References | Shan | Team/Satish | Not Done
Day #2 | 2022-08-17 | Learn about, Git Initialization, code check-in, Repository Browsing | Shan | Team/Satish | Not Done
Day #2 | 2022-08-17 | Lab exercise #2 – Write Simple unit test Program for Calculator Class | Team | Shan/Satish | Not Done

## ExerciseOne
Sr. No. | Action to Perform | Command to use | Validation to do | Remarks
1 | Open Command Window | cmd
2 | Navigate to c:\ drive | cd\
3 | Create new folder under C:\ drive | mkdir c:\LiveExercises
4 | Navigate to newly created folder | cd c:\LiveExercises
5 | Create a Solution File | dotnet new sln | Type DIR to see files created
6 | Create new folder under C:\LiveExercises | mkdir c:\LiveExercises\ExerciseOne
7 | Navigate to newly created folder | cd c:\LiveExercises\ExerciseOne
8 | Create a Console Project | dotnet new console | Type DIR to see files created
9 | Move back to c:\LiveExercises folder | cd..
10 | Launch VS Code from command window | code . | VS code IDE should be Opened
11 | Navigate to Terminal Window | Ctrl+Shift+~ | Termial Window should be Opened
12 | Navigate to ExerciseOne folder | cd .\ExerciseOne\
13 | Build Project | dotnet build | Build succeeded. Should be Displayed
14 | Run Project | dotnet run | Hello World! should be displayed
15 | Move back to c:\LiveExercises folder | cd..
16 | Initialize Source Code Repository | git init
17 | Add Updated/Newly Added files to Git (NOT yet Committed) | git add .\LiveExercises.sln .\ExerciseOne\ExerciseOne.csproj .\ExerciseOne\Program.cs
18 | Commit the files to Git repository | git commit -a -m "project one added"
19
20

## ExerciseTwo
Sr. No. | Action to Perform | Command to use | Validation to do | Remarks
| Open Command Window | cmd
| Navigate to existing folder | cd c:\LiveExercises
| Create new folder under C:\LiveExercises | mkdir c:\LiveExercises\ExerciseTwo
| Navigate to newly created folder | cd c:\LiveExercises\ExerciseTwo
| Create a Class Library Project | dotnet new classlib | Type DIR to see files created
| Move back to c:\LiveExercises folder | cd..
| Add newly Created Project to Solution | dotnet add sln .\ExerciseTwo\ExerciseTwo.csproj
| Launch VS Code from command window | code . | VS code IDE should be Opened
| Navigate to Terminal Window | Ctrl+Shift+~ | Termial Window should be Opened
| Navigate to ExerciseTwo folder | cd .\ExerciseTwo\
| Build Project | dotnet build | Build succeeded. Should be Displayed
| Run Project | dotnet run | Hello World! should be displayed
| Move back to c:\LiveExercises folder | cd..
| Initialize Source Code Repository | git init
| Add Updated/Newly Added files to Git (NOT yet Committed) | git add .\LiveExercises.sln .\ExerciseOne\ExerciseOne.csproj .\ExerciseOne\Program.cs
| Commit the files to Git repository | git commit -a -m "project one added"